## 📌 Milestones
TAQAT.space — Development Master Plan
Next.js 14 (Frontend) · Laravel 11 (Backend) · REST API · PostgreSQL · Redis · 9 Sprints / ~18 Weeks
PHASE LEGEND |  | Phase 1 — Foundation |  | Phase 2 — Core Dashboards |  | Phase 3 — Invoicing & Comms |  | Phase 4 — Admin & Launch
MS # | Milestone Name | Phase | Start (Week) | End (Week) | Duration (Wks) | Sprint(s) | Primary Stack | Key Deliverables | Success Criteria | Owner / Role | Status
M01 | Project Setup & Dev Environment | P1 | 1 | 1 | 1 | S1 | DevOps + BE + FE | Docker Compose, Laravel 11 API skeleton, Next.js 14 App Router + Tailwind + IBM Plex Sans Arabic, PostgreSQL, Redis, GitHub repo + CI scaffold | Both apps boot locally; CI pipeline passes on push; .env templates documented | Lead Dev / DevOps | Todo
M02 | Authentication System (All 3 Roles) | P1 | 1 | 2 | 2 | S1–S2 | BE + FE + API | Users table, role-based Sanctum JWT auth, register (Freelancer + Workspace), login, email verify, password reset; Next.js middleware + protected routes | All 3 roles can register, log in, receive JWT, access role-gated routes; password reset flow end-to-end | BE Dev + FE Dev | Todo
M03 | Database Schema — Core Tables | P1 | 2 | 2 | 1 | S2 | BE + DB | Migrations: workspaces, seats, subscriptions, invoices, internet_packages, booking_requests, messages, announcements, reviews; seeders for dev | All 10 tables created, seeded with realistic test data, relationships verified | BE Dev | Todo
M04 | Public Marketing Site | P2 | 3 | 4 | 2 | S3 | FE + API | Home, Explore (map+list+filters), Workspace Detail, About, FAQ, Contact; bilingual RTL/LTR | Lighthouse performance ≥85; all pages render correctly in AR+EN; filter + map functional | FE Dev | Todo
M05 | Workspace Owner Dashboard — Core | P2 | 4 | 6 | 3 | S3–S4 | BE + FE + API | Dashboard stats, Members management, Seat map (interactive), Booking requests, Space settings | Owner can manage full member lifecycle; seat map reflects real-time state; booking accept/reject flow works | FE Dev + BE Dev | Todo
M06 | Freelancer Dashboard — Core | P2 | 5 | 6 | 2 | S4–S5 | BE + FE + API | Home summary, Explore & search, Subscription detail, Profile edit | Freelancer can discover spaces, request booking, view subscription & assigned seat | FE Dev | Todo
M07 | Invoicing System | P3 | 7 | 9 | 3 | S6 | BE + FE + API | Monthly auto-generation (scheduler), owner issue/track, freelancer view/download, PDF export (DomPDF), manual mark-as-paid, overdue alerts | Monthly cron fires correctly; PDFs render in Arabic + LTR numerals; payment status updates propagate to dashboards | BE Dev + FE Dev | Todo
M08 | Messaging, Notifications & Real-time | P3 | 9 | 11 | 3 | S7 | BE + FE + WS | Direct + broadcast messages, notification center, WebSocket events (Pusher/Soketi), read/unread state | Owner broadcasts reach all members instantly; notification badge updates in real-time; no message loss | BE Dev + FE Dev | Todo
M09 | Announcements, Internet Packages & Reviews | P3 | 10 | 11 | 2 | S7 | BE + FE + API | Announcement CRUD (owner + admin), internet package management, freelancer reviews + ratings | Owner can publish timed announcement; packages assignable; reviews visible on public detail page | BE Dev + FE Dev | Todo
M10 | Super Admin Dashboard | P4 | 12 | 14 | 3 | S8 | BE + FE + API | Platform analytics, workspace approval queue, user management, commissions config, global announcements, platform settings | Admin can approve/reject spaces; commission % propagates to revenue reports; all KPIs accurate | BE Dev + FE Dev | Todo
M11 | Reports, Exports & Advanced Analytics | P4 | 13 | 14 | 2 | S8 | BE + FE | Revenue & occupancy reports (charts), Excel export (owner), PDF invoices, admin financial reports | All exports downloadable; charts match DB aggregates; date range filters work | BE Dev + FE Dev | Todo
M12 | Testing, Hardening & Production Launch | P4 | 15 | 18 | 4 | S9 | Testing + DevOps | PHPUnit feature tests (≥80% coverage), Playwright E2E tests, load testing, DigitalOcean prod deployment, SSL, Sentry, Uptime monitoring, backup policy | Zero critical bugs in prod; p95 API latency <300ms; all E2E tests green; monitoring dashboards live | Lead Dev + DevOps | Todo

## 🗂 Backlog
TAQAT.space — Full Development Backlog
Task ID | Module | Sub-feature / Task Name | Type | Priority | SP | Phase | Sprint | Depends On | Backend Scope | Frontend Scope | API Endpoint(s) | Status
T001 | DevOps | Next.js 14 project init (App Router, TS, Tailwind, IBM Plex Arabic, RTL config) | FE | P1 | 3 | P1 | S1 | — | — | npx create-next-app, next-intl, dir=rtl | — | Todo
T002 | DevOps | Laravel 11 API-only project init (CORS, Sanctum, .env template) | BE | P1 | 3 | P1 | S1 | — | laravel new --git, api.php routes, cors config | — | — | Todo
T003 | DevOps | Docker Compose: PostgreSQL, Redis, Nginx, Laravel, Next.js | DevOps | P1 | 5 | P1 | S1 | T001,T002 | docker-compose.yml, healthchecks | — | — | Todo
T004 | DevOps | GitHub Actions CI: lint + test on PR for both repos | DevOps | P1 | 3 | P1 | S1 | T003 | phpunit in pipeline | eslint, tsc --noEmit | — | Todo
T005 | DevOps | Redis configuration (cache driver + queue driver) | DevOps | P1 | 2 | P1 | S1 | T003 | CACHE_DRIVER=redis, QUEUE_CONNECTION=redis | — | — | Todo
T006 | Database | Core schema migrations: users (role enum: freelancer/workspace_owner/admin) | DB | P1 | 3 | P1 | S2 | T003 | php artisan make:migration, role ENUM | — | — | Todo
T007 | Database | Migrations: workspaces, seats, subscriptions, invoices | DB | P1 | 5 | P1 | S2 | T006 | 4 migration files + models | — | — | Todo
T008 | Database | Migrations: internet_packages, booking_requests, messages, announcements, reviews | DB | P1 | 5 | P1 | S2 | T007 | 4 migration files + models | — | — | Todo
T009 | Database | Database seeders: realistic Gaza test data (spaces, users, seats) | DB | P1 | 3 | P1 | S2 | T007,T008 | DatabaseSeeder.php + factories | — | — | Todo
T010 | Auth BE | Sanctum auth: register endpoint (3 roles, file upload for docs) | BE | P1 | 5 | P1 | S2 | T006 | RegisterController, FormRequest validation | — | POST /api/auth/register | Todo
T011 | Auth BE | Sanctum auth: login, logout, token refresh | BE | P1 | 3 | P1 | S2 | T010 | AuthController, token generation | — | POST /api/auth/login, /logout | Todo
T012 | Auth BE | Email verification + password reset (queue-based Mailgun) | BE | P1 | 3 | P1 | S2 | T011 | MustVerifyEmail, PasswordReset, Mailgun driver | — | POST /api/auth/forgot-password, /reset | Todo
T013 | Auth BE | Role-based gates + middleware (freelancer, workspace_owner, admin) | BE | P1 | 3 | P1 | S2 | T011 | Gates::define, RoleMiddleware | — | — | Todo
T014 | Auth FE | Next.js auth layer: middleware.ts, protected route HOC, token storage (httpOnly cookie) | FE | P1 | 5 | P1 | S2 | T011 | — | middleware.ts, useAuth hook, AuthProvider | — | Todo
T015 | Auth FE | Login page (bilingual RTL/LTR, error states) | FE | P1 | 3 | P1 | S2 | T014 | — | app/(auth)/login/page.tsx | POST /api/auth/login | Todo
T016 | Auth FE | Register as Freelancer (3-step: personal → specialty → ID upload) | FE | P1 | 5 | P1 | S2 | T014 | — | app/(auth)/register/freelancer/page.tsx | POST /api/auth/register | Todo
T017 | Auth FE | Register as Workspace (4-step: info → location → seats & pricing → docs) | FE | P1 | 5 | P1 | S2 | T014 | — | app/(auth)/register/workspace/page.tsx + pending-review screen | POST /api/auth/register | Todo
T018 | Auth FE | Forgot password + reset password pages | FE | P1 | 2 | P1 | S2 | T012 | — | app/(auth)/forgot / reset pages | POST /api/auth/forgot-password | Todo
T019 | Public FE | Home page: hero, stat tiles, featured workspaces, how-it-works, dual CTA | FE | P2 | 5 | P2 | S3 | T014 | — | app/(public)/page.tsx, components/FeaturedGrid | GET /api/workspaces?featured=1 | Todo
T020 | Public FE | Explore workspaces: list + Leaflet map, advanced filters (city, price, amenities, rating) | FE | P2 | 8 | P2 | S3 | T019 | — | app/(public)/explore, FilterBar, MapView | GET /api/workspaces | Todo
T021 | Public FE | Workspace detail page: gallery, amenities, pricing, reviews, book CTA | FE | P2 | 5 | P2 | S3 | T020 | — | app/(public)/workspaces/[id]/page.tsx | GET /api/workspaces/:id | Todo
T022 | Public FE | About, FAQ (role-segmented), Contact pages | FE | P2 | 2 | P2 | S3 | T019 | — | app/(public)/(info) pages | — | Todo
T023 | Workspaces BE | Workspaces API: CRUD (owner), public list + detail (public), status management (admin) | BE | P2 | 5 | P2 | S3 | T013 | WorkspaceController, Resource, Policy | — | GET /api/workspaces, POST/PUT/DELETE | Todo
T024 | Workspaces BE | Workspace public search: filter by city, price range, amenities (JSON field), rating avg | BE | P2 | 5 | P2 | S3 | T023 | Query scopes on Workspace model | — | GET /api/workspaces?city=&min_price=&amenities= | Todo
T025 | Workspaces BE | File storage for workspace photos (S3 / R2 via Flysystem) | BE | P2 | 3 | P2 | S3 | T023 | Flysystem disk config, PhotoController | — | POST /api/workspaces/:id/photos | Todo
T026 | Seats BE | Seats API: CRUD, assign to member, seat-map state endpoint | BE | P2 | 5 | P2 | S3 | T023 | SeatController, SeatResource | — | GET /api/workspaces/:id/seats, PUT /api/seats/:id/assign | Todo
T027 | Owner Dashboard | Owner dashboard home: occupancy %, today revenue, active members, pending requests (stat tiles) | FE+BE | P2 | 5 | P2 | S4 | T023,T026 | DashboardController aggregates | app/(dashboard)/owner/page.tsx, StatTile | GET /api/workspace/dashboard | Todo
T028 | Owner Dashboard | Members management: table, filter/search, accept/suspend, member detail drawer | FE+BE | P2 | 8 | P2 | S4 | T010,T027 | MemberController, status transitions | app/(dashboard)/owner/members | GET/PUT /api/workspace/members | Todo
T029 | Owner Dashboard | Interactive seat map: grid of tile components (available/occupied/selected/disabled states) | FE | P2 | 8 | P2 | S4 | T026 | — | components/SeatMap (tile primitives), drag-assign | GET /api/workspaces/:id/seats | Todo
T030 | Owner Dashboard | Seat assignment flow: assign seat to member from seat map, confirmation modal | FE+BE | P2 | 5 | P2 | S4 | T028,T029 | SeatController::assign, validation | components/AssignModal | PUT /api/seats/:id/assign | Todo
T031 | Owner Dashboard | Booking requests: incoming queue, approve (assign seat) / reject with reason | FE+BE | P2 | 5 | P2 | S4 | T026 | BookingRequestController | app/(dashboard)/owner/bookings | GET/PUT /api/workspace/booking-requests | Todo
T032 | Owner Dashboard | Space settings: edit info, photos, hours, pricing, amenities | FE+BE | P2 | 5 | P2 | S4 | T023 | WorkspaceController::update | app/(dashboard)/owner/settings | PUT /api/workspace/settings | Todo
T033 | Freelancer Dashboard | Freelancer home: subscription status, assigned seat, next invoice, notification summary | FE+BE | P2 | 3 | P2 | S4 | T014,T026 | MemberDashboardController | app/(dashboard)/freelancer/page.tsx | GET /api/member/dashboard | Todo
T034 | Freelancer Dashboard | My subscription & bookings: current plan, renewal, cancel/change request | FE+BE | P2 | 5 | P2 | S4 | T033 | SubscriptionController | app/(dashboard)/freelancer/subscription | GET/PUT /api/member/subscriptions | Todo
T035 | Freelancer Dashboard | Freelancer profile: edit personal info, avatar upload, specialty, change password | FE+BE | P2 | 3 | P2 | S5 | T033 | UserController::update | app/(dashboard)/freelancer/profile | PUT /api/member/profile | Todo
T036 | Booking BE | Booking request submit (freelancer) + auto-notify owner | BE | P2 | 5 | P2 | S5 | T031 | BookingRequestController::store, notify owner | — | POST /api/booking-requests | Todo
T037 | Booking BE | Booking approval flow: accept (create subscription + assign seat) / reject logic | BE | P2 | 5 | P2 | S5 | T036 | BookingRequest state machine, SubscriptionFactory | — | PUT /api/workspace/booking-requests/:id | Todo
T038 | Internet Packages | Internet packages CRUD (owner): add package, set speed/data/price/unlimited flag | FE+BE | P3 | 3 | P3 | S5 | T023 | PackageController | app/(dashboard)/owner/internet | POST/PUT/DELETE /api/workspace/packages | Todo
T039 | Internet Packages | Assign internet package to member; track assignment | FE+BE | P3 | 3 | P3 | S5 | T038 | PackageMember pivot, subscription link | components/PackageAssign | PUT /api/workspace/packages/:id/assign | Todo
T040 | Invoicing BE | Monthly invoice auto-generation: Laravel scheduler creates invoice per active subscription on 1st | BE | P3 | 8 | P3 | S6 | T037 | InvoiceController, app/Console/Kernel, cron | — | — | Todo
T041 | Invoicing BE | Invoice model: paid/pending/overdue status, due_date, paid_at tracking | BE | P3 | 3 | P3 | S6 | T040 | Invoice model, status ENUM, scopes | — | GET/POST /api/workspace/invoices | Todo
T042 | Invoicing BE | Manual mark-as-paid by owner; webhook stub for future payment gateway | BE | P3 | 3 | P3 | S6 | T041 | InvoiceController::markPaid | — | PUT /api/workspace/invoices/:id/pay | Todo
T043 | Invoicing BE | Overdue detection: auto-flag invoice after due_date + send warning notification (queue) | BE | P3 | 3 | P3 | S6 | T041 | InvoiceOverdueJob, scheduler daily | — | — | Todo
T044 | Invoicing BE | PDF generation: Arabic invoice PDF (DomPDF + Blade template, LTR numerals in RTL doc) | BE | P3 | 5 | P3 | S6 | T041 | DomPDF, invoice.blade.php (AR+EN) | — | GET /api/invoices/:id/pdf | Todo
T045 | Invoicing FE | Owner invoices dashboard: issue, view, filter, status badges, send reminder, PDF download | FE | P3 | 8 | P3 | S6 | T042,T044 | — | app/(dashboard)/owner/invoices | GET /api/workspace/invoices | Todo
T046 | Invoicing FE | Freelancer invoices: full history, status, PDF download | FE | P3 | 5 | P3 | S6 | T041 | — | app/(dashboard)/freelancer/invoices | GET /api/member/invoices | Todo
T047 | Invoicing FE | Invoice alert cards on both dashboards (overdue/pending callout) | FE | P3 | 2 | P3 | S6 | T045,T046 | — | components/InvoiceAlert | — | Todo
T048 | Messaging BE | Messages table: sender, receiver, workspace context, type (direct/broadcast), read_at | BE | P3 | 3 | P3 | S7 | T008 | MessageController, Message model | — | POST /api/workspace/messages | Todo
T049 | Messaging BE | Broadcast message to all workspace members (single send → fan-out) | BE | P3 | 3 | P3 | S7 | T048 | MessageController::broadcast, Queue | — | POST /api/workspace/messages/broadcast | Todo
T050 | Real-time | Pusher/Soketi WebSocket setup: Laravel Broadcasting + Next.js Pusher-js client | DevOps | P3 | 5 | P3 | S7 | T048 | BROADCAST_DRIVER=pusher, events/channels | lib/pusher.ts, useChannel hook | — | Todo
T051 | Real-time | Broadcast events: NewMessage, NewNotification, InvoiceDue — via presence/private channels | BE | P3 | 5 | P3 | S7 | T050 | Event classes, channel auth | — | — | Todo
T052 | Notifications BE | Notifications table (DB channel): polymorphic notifiable, read_at, type | BE | P3 | 3 | P3 | S7 | T008 | Laravel Notification, DatabaseChannel | — | GET /api/notifications, PUT /read | Todo
T053 | Notifications FE | Notification center: bell + unread badge, list, mark read, filter by type | FE | P3 | 5 | P3 | S7 | T052 | — | components/NotificationCenter, app/(dashboard)/*/notifications | GET /api/notifications | Todo
T054 | Messaging FE | Owner messages UI: thread list, individual + broadcast compose, read receipts | FE | P3 | 5 | P3 | S7 | T049,T051 | — | app/(dashboard)/owner/messages, MessageThread | GET /api/workspace/messages | Todo
T055 | Announcements BE | Announcements CRUD: workspace-scoped, type (offer/info/alert), schedule, expiry | BE | P3 | 3 | P3 | S7 | T008 | AnnouncementController, published_at/expires_at | — | POST/GET /api/workspace/announcements | Todo
T056 | Announcements FE | Owner announcements: create (type + schedule), manage list | FE | P3 | 3 | P3 | S7 | T055 | — | app/(dashboard)/owner/announcements | — | Todo
T057 | Reviews BE | Reviews: submit (freelancer only, post-subscription), list per workspace, avg rating update | BE | P3 | 3 | P3 | S7 | T008 | ReviewController, avg_rating denorm on workspaces | — | POST /api/reviews, GET /api/workspaces/:id/reviews | Todo
T058 | Reviews FE | Workspace detail: reviews section + rating stars + submit review modal | FE | P3 | 2 | P3 | S7 | T057 | — | app/(public)/workspaces/[id] — ReviewSection | POST /api/reviews | Todo
T059 | Admin BE | Admin: workspace approval queue (approve/reject with email notify) | BE | P4 | 5 | P4 | S8 | T023 | WorkspaceController@updateStatus, AdminPolicy | — | PUT /api/admin/workspaces/:id/status | Todo
T060 | Admin BE | Admin: user management — list all, enable/disable, view activity | BE | P4 | 3 | P4 | S8 | T013 | AdminUserController | — | GET/PUT /api/admin/users | Todo
T061 | Admin BE | Admin: platform analytics aggregation (total spaces, members, gross revenue, occupancy avg) | BE | P4 | 5 | P4 | S8 | T040,T057 | AnalyticsController, DB aggregates | — | GET /api/admin/analytics | Todo
T062 | Admin BE | Admin: commission config (% per workspace), commissions log table | BE | P4 | 5 | P4 | S8 | T041 | Commission model, CommissionController | — | GET/POST /api/admin/commissions | Todo
T063 | Admin BE | Admin: global announcement broadcast to entire platform | BE | P4 | 3 | P4 | S8 | T055 | AnnouncementController@globalBroadcast | — | POST /api/admin/announcements | Todo
T064 | Admin FE | Admin dashboard: platform stat tiles + revenue line chart + occupancy gauge | FE | P4 | 5 | P4 | S8 | T061 | — | app/(dashboard)/admin/page.tsx, Recharts | GET /api/admin/analytics | Todo
T065 | Admin FE | Admin workspace management: approval queue, reject modal, detail panel | FE | P4 | 5 | P4 | S8 | T059 | — | app/(dashboard)/admin/workspaces | PUT /api/admin/workspaces/:id/status | Todo
T066 | Admin FE | Admin user management: table, filter by role, enable/disable | FE | P4 | 3 | P4 | S8 | T060 | — | app/(dashboard)/admin/users | GET/PUT /api/admin/users | Todo
T067 | Admin FE | Admin finance & commissions: config panel + transfer log | FE | P4 | 3 | P4 | S8 | T062 | — | app/(dashboard)/admin/finance | GET/POST /api/admin/commissions | Todo
T068 | Admin FE | Admin platform settings: pricing plans, language defaults, timezone | FE | P4 | 2 | P4 | S8 | T060 | — | app/(dashboard)/admin/settings | PUT /api/admin/settings | Todo
T069 | Reports | Owner reports: monthly revenue chart, occupancy rate, top members, Excel export (Maatwebsite) | FE+BE | P4 | 5 | P4 | S8 | T040,T028 | ReportController, Excel facade | app/(dashboard)/owner/reports | GET /api/workspace/reports, /export | Todo
T070 | Reports | Admin financial reports with commission breakdown; date-range filter | FE+BE | P4 | 5 | P4 | S8 | T062 | AdminReportController | app/(dashboard)/admin/reports | GET /api/admin/reports | Todo
T071 | Testing | Laravel PHPUnit: Auth feature tests (register, login, role gates) | Testing | P4 | 5 | P4 | S9 | T013 | tests/Feature/AuthTest.php | — | — | Todo
T072 | Testing | Laravel PHPUnit: Invoicing tests (auto-generate, mark paid, overdue job) | Testing | P4 | 5 | P4 | S9 | T040,T043 | tests/Feature/InvoiceTest.php | — | — | Todo
T073 | Testing | Laravel PHPUnit: Booking + subscription lifecycle tests | Testing | P4 | 5 | P4 | S9 | T037 | tests/Feature/BookingTest.php | — | — | Todo
T074 | Testing | Playwright E2E: register freelancer → discover space → submit booking | Testing | P4 | 5 | P4 | S9 | T036 | — | e2e/booking-flow.spec.ts | — | Todo
T075 | Testing | Playwright E2E: owner approve booking → issue invoice → freelancer downloads PDF | Testing | P4 | 5 | P4 | S9 | T044,T046 | — | e2e/invoice-flow.spec.ts | — | Todo
T076 | Testing | API load test (k6): /api/workspaces list + /api/member/dashboard under 100 VU | Testing | P4 | 3 | P4 | S9 | T024,T033 | — | k6/load-test.js | — | Todo
T077 | DevOps | Production: DigitalOcean Droplet provisioning, Nginx, SSL (Let's Encrypt), PM2 / Supervisor | DevOps | P4 | 5 | P4 | S9 | T003 | Nginx config, Supervisor for queue worker | next build, NODE_ENV=production | — | Todo
T078 | DevOps | Environment hardening: secrets management, DB backups (daily cron → S3) | DevOps | P4 | 3 | P4 | S9 | T077 | .env encryption, mysqldump/pg_dump cron | — | — | Todo
T079 | DevOps | Sentry integration (Laravel + Next.js), Uptime monitoring (UptimeRobot / BetterUptime) | DevOps | P4 | 3 | P4 | S9 | T077 | Sentry DSN, error capture | Sentry client SDK | — | Todo
T080 | DevOps | Staging deploy + smoke-test checklist before prod cutover | DevOps | P4 | 3 | P4 | S9 | T074,T075 | — | — | — | Todo
Total Story Points |  |  |  |  | 335

## 🏃 Sprint Plan
TAQAT.space — Sprint Plan · 9 Sprints · 2 Weeks Each · ~18 Weeks Total
Sprint | Weeks | Phase | Sprint Goal | Task IDs | Story Points | FE Deliverables | BE / API Deliverables | DevOps / Infra | Definition of Done | Capacity Note
S1 | Wk 1–2 | P1 | Boot both apps. Dev environment live. CI green. | T001–T005 | 16 | Next.js 14 running, Tailwind + IBM Plex Arabic, RTL layout shell | Laravel 11 API skeleton, CORS, Sanctum installed, .env template | Docker Compose up (Postgres, Redis, Nginx), GitHub Actions CI | Both apps boot locally; CI passes on push to main; team can onboard in <10 min | 1–2 devs. Heaviest DevOps sprint — block enough time for Docker networking issues.
S2 | Wk 3–4 | P1 | Authentication complete for all 3 roles. DB schema fully migrated. | T006–T018 | 50 | Login, Freelancer register (3-step), Workspace register (4-step), forgot/reset pages | users table + 9 other migrations, Sanctum auth endpoints, role gates, email queue | Mailgun config, S3/R2 bucket for file uploads | All 3 roles can register + log in; JWT issued; role-protected routes enforced; password reset email delivers | Critical auth sprint — no Sprint 3 work should start until T013 (gates) is done.
S3 | Wk 5–6 | P2 | Public marketing site live. Workspace API + search functional. | T019–T026 | 38 | Home, Explore (map + filters), Workspace detail, About/FAQ/Contact — bilingual | WorkspaceController (CRUD + public search), SeatController, photo storage | Leaflet map tile config, CDN for workspace photos | Public pages render correctly in AR + EN; filter returns correct results; Lighthouse ≥80 | FE-heavy sprint. Leaflet + RTL map UI is the risk item — spike early.
S4 | Wk 7–8 | P2 | Owner dashboard core live: members, seat map, booking requests, settings. | T027–T032 | 44 | Owner dashboard home, members table, interactive seat map, booking queue, settings page | DashboardController aggregates, MemberController, BookingRequestController, seat assign logic | — | Owner can perform full member lifecycle; seat map renders correct state from API; booking approve creates subscription | Seat map (T029) is highest complexity task. Allocate 8 SP / ~2 days to it.
S5 | Wk 9–10 | P2→P3 | Freelancer dashboard complete. Booking flow end-to-end. Internet packages. | T033–T039 | 19 | Freelancer home, subscription detail, profile edit, explore (reuse public components) | MemberDashboardController, SubscriptionController, BookingRequest submit, PackageController | — | Full booking flow works end-to-end: freelancer submits → owner approves → subscription + seat created | Integration sprint — FE and BE must coordinate on booking state machine. Plan a mid-sprint sync.
S6 | Wk 11–12 | P3 | Invoicing system fully operational. PDFs bilingual. Overdue detection running. | T040–T047 | 37 | Owner invoices dashboard, freelancer invoice history, PDF download, alert cards | Laravel Scheduler (monthly), InvoiceController, DomPDF Blade template (AR+EN), overdue job | Cron scheduler verified in prod-like env, DomPDF installed | Monthly cron fires and creates correct invoices; PDF renders Arabic correctly; overdue flag updates within 24h | DomPDF Arabic RTL rendering is a known pain point — budget extra time. Test on real data from seeders.
S7 | Wk 13–14 | P3 | Real-time messaging, notifications, announcements, and reviews live. | T048–T058 | 40 | Messages UI (owner), notification center (both roles), announcements (owner), review section (public detail) | MessageController, broadcast fan-out, Laravel Events, Notification DB channel, Review + rating update | Pusher/Soketi WebSocket server configured; private channels auth route | Real-time message appears in <500ms; notification badge updates without page refresh; reviews visible on public page | WebSocket infra (T050) is the risk. Use Pusher cloud for dev/staging to avoid Soketi self-host complexity until Sprint 9.
S8 | Wk 15–16 | P4 | Super Admin dashboard complete. Reports + Excel exports live. | T059–T070 | 49 | Admin: analytics, workspace approval, user mgmt, commissions, global announcements; Owner reports + Excel export | AdminControllers (workspace/user/commission/analytics/reports), Maatwebsite Excel export | — | Admin can approve workspaces; KPIs match DB aggregates; Excel export downloads with correct data | Commission model (T062) has business logic implications — validate formula with founder before building.
S9 | Wk 17–18 | P4 | Full test coverage. Hardened for production. Go-live. | T071–T080 | 42 | Playwright E2E suites green; staging smoke-test passed | PHPUnit feature tests ≥80% coverage; k6 load test passes (<300ms p95) | DigitalOcean prod Droplet, Nginx + SSL, Supervisor queue worker, Sentry, UptimeRobot, DB backup cron | Zero P1 bugs; all E2E tests pass; Sentry live in prod; uptime monitor configured; team sign-off | Do NOT start prod deploy until staging smoke-test passes. Keep a rollback plan (Deployer or git tag revert).

## 🔌 API Contracts
TAQAT.space — API Contract Reference (Laravel 11 → Next.js 14)
# | Group | Method | Endpoint | Auth | Role(s) | Description | Key Request Params | Response Shape | Sprint
1 | Auth | POST | /api/auth/register | — | All | Register user (role in body); workspace role queues for admin approval | name, email, password, role, [specialty], [files] | { user, token, role } | S2
2 | Auth | POST | /api/auth/login | — | All | Login + return Sanctum token | email, password | { user, token, expires_at } | S2
3 | Auth | POST | /api/auth/logout | Bearer | All | Invalidate token | — | { message } | S2
4 | Auth | POST | /api/auth/forgot-password | — | All | Send reset link via Mailgun | email | { message } | S2
5 | Auth | POST | /api/auth/reset-password | — | All | Reset password | token, email, password | { message } | S2
6 | Public | GET | /api/workspaces | — | Public | List workspaces (paginated). Supports: city, min_price, max_price, amenities[], min_rating, search | Query params above | { data: Workspace[], meta: Pagination } | S3
7 | Public | GET | /api/workspaces/:id | — | Public | Full workspace detail with seats summary, amenities, photos, avg rating | — | { Workspace + seats_summary + recent_reviews } | S3
8 | Public | GET | /api/workspaces/:id/reviews | — | Public | Reviews for a workspace | page, per_page | { data: Review[], meta } | S7
9 | Booking | POST | /api/booking-requests | Bearer | Freelancer | Submit booking request | workspace_id, preferred_seat_type, message | { booking_request } | S5
10 | Booking | GET | /api/workspace/booking-requests | Bearer | Owner | List incoming booking requests | status (pending/approved/rejected) | { data: BookingRequest[] } | S4
11 | Booking | PUT | /api/workspace/booking-requests/:id | Bearer | Owner | Approve (assigns seat + creates subscription) or reject | action (approve/reject), seat_id, rejection_reason | { booking_request, [subscription] } | S5
12 | Owner | GET | /api/workspace/dashboard | Bearer | Owner | Aggregated dashboard stats (occupancy, revenue today, active members, pending items) | — | { stats: { occupancy_pct, revenue_today, active_members, pending_requests, overdue_invoices } } | S4
13 | Owner | GET | /api/workspace/members | Bearer | Owner | List workspace members with subscription status | status, search, page | { data: Member[] } | S4
14 | Owner | PUT | /api/workspace/members/:id/status | Bearer | Owner | Activate or suspend member account | status (active/suspended) | { member } | S4
15 | Owner | GET | /api/workspaces/:id/seats | Bearer | Owner/Public | Seat map state (all seats + status + assignee) | — | { seats: Seat[] } | S4
16 | Owner | PUT | /api/seats/:id/assign | Bearer | Owner | Assign seat to a member | member_id | { seat } | S4
17 | Owner | POST | /api/workspace/invoices | Bearer | Owner | Manually issue invoice (outside monthly auto) | subscription_id, amount, due_date | { invoice } | S6
18 | Owner | GET | /api/workspace/invoices | Bearer | Owner | List invoices with status filter | status, month, page | { data: Invoice[] } | S6
19 | Owner | PUT | /api/workspace/invoices/:id/pay | Bearer | Owner | Mark invoice as paid | paid_at (optional, defaults now) | { invoice } | S6
20 | Owner | GET | /api/invoices/:id/pdf | Bearer | Owner/Freelancer | Stream invoice PDF | — | application/pdf binary | S6
21 | Owner | POST | /api/workspace/messages | Bearer | Owner | Send direct or broadcast message | receiver_id (null=broadcast), content, type | { message } | S7
22 | Owner | POST | /api/workspace/announcements | Bearer | Owner | Create announcement (offer/info/alert, optional schedule) | title, body, type, published_at, expires_at | { announcement } | S7
23 | Owner | GET | /api/workspace/reports | Bearer | Owner | Monthly revenue & occupancy report (date range) | from, to | { revenue_by_month[], occupancy_by_month[], top_members[] } | S8
24 | Owner | GET | /api/workspace/reports/export | Bearer | Owner | Excel export of report | from, to | application/xlsx binary | S8
25 | Owner | POST | /api/workspace/packages | Bearer | Owner | Create internet package | name, speed_mbps, price, data_limit_gb, is_unlimited | { package } | S5
26 | Owner | PUT | /api/workspace/packages/:id/assign | Bearer | Owner | Assign internet package to member | member_id | { assignment } | S5
27 | Member | GET | /api/member/dashboard | Bearer | Freelancer | Freelancer home summary | — | { subscription, seat, next_invoice, unread_notifications } | S4
28 | Member | GET | /api/member/subscriptions | Bearer | Freelancer | Freelancer subscription list (current + history) | — | { data: Subscription[] } | S5
29 | Member | GET | /api/member/invoices | Bearer | Freelancer | Freelancer invoices | status, page | { data: Invoice[] } | S6
30 | Member | PUT | /api/member/profile | Bearer | Freelancer | Update profile (name, specialty, avatar) | name, specialty, avatar (file) | { user } | S5
31 | Member | POST | /api/reviews | Bearer | Freelancer | Submit review for workspace (post-subscription only) | workspace_id, rating (1–5), comment | { review } | S7
32 | Notifications | GET | /api/notifications | Bearer | All | List notifications (paginated, unread count) | read, page | { data: Notification[], unread_count } | S7
33 | Notifications | PUT | /api/notifications/read | Bearer | All | Mark notifications as read | ids[] or all=true | { updated_count } | S7
34 | Admin | GET | /api/admin/analytics | Bearer | Admin | Platform-wide analytics aggregates | from, to | { total_workspaces, total_members, gross_revenue, avg_occupancy, growth_charts } | S8
35 | Admin | GET | /api/admin/workspaces | Bearer | Admin | All workspaces (any status) with owner info | status, search, page | { data: Workspace[] } | S8
36 | Admin | PUT | /api/admin/workspaces/:id/status | Bearer | Admin | Approve, reject, or suspend workspace | status, reason | { workspace } | S8
37 | Admin | GET | /api/admin/users | Bearer | Admin | All users, filterable by role/status | role, status, search | { data: User[] } | S8
38 | Admin | PUT | /api/admin/users/:id/status | Bearer | Admin | Enable or disable any user account | status | { user } | S8
39 | Admin | GET | /api/admin/commissions | Bearer | Admin | Commission config + transfer log | — | { rate_pct, transfers[] } | S8
40 | Admin | POST | /api/admin/commissions | Bearer | Admin | Set platform commission rate | rate_pct | { commission_config } | S8
41 | Admin | POST | /api/admin/announcements | Bearer | Admin | Broadcast global announcement to all users | title, body, type | { announcement } | S8

## ⚙️ Tech Stack
TAQAT.space — Tech Stack & Architecture Reference
Layer | Choice | Alt / Fallback | Purpose | Version | Notes
Frontend | Next.js 14 | Remix | App Router, SSR/SSG, API routes for BFF proxy | 14.x | Use App Router only. Pages Router = deprecated for this project.
Frontend | TypeScript | — | Type safety across entire FE | 5.x | Strict mode on.
Frontend | Tailwind CSS | — | Utility-first styling; RTL via `dir` attribute on <html> | 3.x | Add `rtl:` variant utilities.
Frontend | IBM Plex Sans Arabic | Tajawal | Primary Arabic typeface; Inter for Latin/numerals | Variable | Load via next/font for perf.
Frontend | next-intl | next-i18next | Bilingual AR (default, RTL) + EN (LTR) | 3.x | Locale in URL prefix: /ar, /en
Frontend | Pusher-js | — | WebSocket client for real-time notifications + messages | 8.x | Use Pusher Sandbox (free) in dev.
Frontend | Leaflet (react-leaflet) | Mapbox GL | Workspace map on explore page | 4.x | OpenStreetMap tiles — free, no API key.
Frontend | Recharts | Chart.js | Dashboard charts (revenue, occupancy) | 2.x | Composable, TS-native.
Frontend | React Hook Form + Zod | Formik | All forms — validation + type inference | — | Zod schema shared with backend DTO shapes.
Backend | Laravel 11 | — | API-only (no Blade views except invoice PDF) | 11.x | Use api.php routes only. No web.php except auth callbacks.
Backend | PHP | — | Runtime | 8.3+ | Use typed properties, readonly classes, enums.
Backend | Laravel Sanctum | Passport | SPA token authentication (Bearer JWT) | — | httpOnly cookie in prod for Next.js SPA calls.
Backend | Laravel Queues | — | Email, notifications, overdue invoice jobs, PDF generation | — | QUEUE_CONNECTION=redis in prod.
Backend | Laravel Scheduler | — | Monthly invoice auto-generation, overdue detection | — | Cron: * * * * * php artisan schedule:run
Backend | DomPDF (laravel-dompdf) | mPDF | Arabic invoice PDF generation | 2.x | Requires RTL-capable font embedded in PDF.
Backend | Maatwebsite Excel | PHP Spreadsheet | Excel report exports | 3.x | Use chunk reading for large datasets.
Backend | Spatie Laravel Permission | — | Role & permission management on top of Sanctum | 6.x | Roles: freelancer, workspace_owner, admin.
Backend | Laravel Broadcasting | — | WebSocket event dispatch | — | Driver: pusher (prod), log (dev).
Database | PostgreSQL | MySQL | Primary relational DB | 15+ | Use JSONB for amenities[] column on workspaces.
Database | Redis | Memcached | Cache + queue backend + session | 7.x | Use separate DBs: 0=cache, 1=queue, 2=session.
Storage | Cloudflare R2 (via Flysystem S3) | DigitalOcean Spaces | Workspace photos, ID docs, invoice PDFs | — | R2 = S3-compatible, zero egress fees.
Infrastructure | DigitalOcean Droplet | Hetzner VPS | Production hosting | — | Start: $24/mo 4GB RAM Droplet. Scale to managed DB when traffic grows.
Infrastructure | Nginx | Caddy | Reverse proxy, SSL termination | — | Two server blocks: api.taqat.space + taqat.space
Infrastructure | Supervisor | PM2 | Laravel queue worker process manager | — | 4 worker processes per Droplet.
DevOps | GitHub Actions | GitLab CI | CI: lint, test, deploy on push to main | — | Separate workflows: FE (npm test) + BE (phpunit).
DevOps | Docker Compose | — | Local development environment | — | Prod does NOT use Docker — bare metal Droplet.
Monitoring | Sentry | Bugsnag | Error tracking (FE + BE) | — | Set up before any prod traffic.
Monitoring | UptimeRobot | BetterUptime | Uptime + response-time monitoring | — | Monitor /api/health endpoint.
Email | Mailgun | SendGrid | Transactional email | — | Verify taqat.space domain in Mailgun. AR email templates.
Payments | Manual tracking (MVP) | Tap Payments | Invoice payment (manual mark-paid in MVP; gateway in v2) | — | Tap Payments is the best regional gateway. Integrate in v2 Sprint.